## Overview
Carborn Home Challenge Test Completion Report
Test Type | System Testing | Project / BAU | Project
Project Name | Carbon Home Challenge | Project Owner | Carbon
Business Owner | Carbon | IT Resource Company
Test Design Start Date | 2021-03-01 | Test Design End Date | 2021-03-01
Test Execution Start Date | 2021-03-01 | Test Execution End Date | 2021-03-03
Sign Off
Name | Role | Date | Signature
Charles Enebeli | IT Test Analyst
Business Analyst
Product Manager
Project Manager
Product Sponsor

## Test Summary
Project Name | Digital Banking |  | Business Owner |  | Carbon
Project Manager | Eteanwan Solomon |  | Test Company |  | Hyperion Global Services
2021-03-03 | Total Tests |  | Outstanding |  | Completed
| 8 |  | 0 |  | 8
| Total Defects |  | Outstanding |  | Closed
| 2 |  | 2 |  | 0
RAG Status | No passed / % Pass Rate) |  | 6
Green | No of Defects / % of Critical & High) |  | 0
Exit Criteria | Achieved | Comments
100% test coverage | Yes | None
Critical Defects Closed | No | See Defects Sheet | [5 empty] | Overview of Key Testing Issues
High Defect Open | No | See Defects Sheet | [5 empty] | A number of issues were observed during Sysytem Test of the Digital Banking Application and made known to the relevant Stakeholders in an email; these issues are listed below: 1. The instability of the Test environment which unfortunately necessitated our request for multiply Test Account profile 2. The APK supplied and/or deployed on Test had features that needed Third Party integration for verification and validation but were breaking and/or not implemented
Business Walkthrough | Yes
Execution Statistics | Total Test Cases | Passed | Failed | Not Started | Not Applicable | In Progress | On Hold
Number of tests | 8 | 6 | 2 | 0 | 0 | 0 | 0
Defect Statistics |  | Critical | High | Medium | Low | Total
Raised & Outstanding |  | 1 | 1 |  |  | 2
Closed
Total |  | 1 | 1 |  |  | 2

## Test Case
Pre-requisite
Pass Criteria: | The system behaviour matches the expected results column
Testers Name(s): | Charles Enebeli
Build
Created by:
Actors: | IT QA
TEST CASE NUMBER | FEATURES | TEST CASES | EXPECTED RESULT | ACTUAL RESULT | PASS/FAIL | COMMENTS | TEST TYPE
CHC001 | Login | Verify that User can login with valid credentials | User should be able to login successfully with a valid credentials | User was able to login successfully with a valid credentials | PASS |  | System Test
CHC002 |  | Verify that User can not log in with invalid credentials | User should not be able to login successfully with an invalid credentials | User was not able to login successfully with an invalid credentials | PASS |  | System Test
CHC003 | Fund Wallet | Verify that User can fund wallet using Existing Card | The User should be able to fund wallet using Existing Card | "Wallet is not available to receive funds was displayed" was displayed | FAIL | Wallet could not be funded | System Test
CHC004 | Airtime Recharge | Verify that User can select saved beneficiaries if available | The User should be able to select from saved beneficiaries | User was able to select a beneficiary from the list | PASS |  | System Test
CHC005 |  | Verify that User can select amount | The User should be able to select their desired amount | The User was able to select their desired amount | PASS |  | System Test
CHC006 |  | Verify that user can select service provider | The user should be able to select service provider | The user was able to select service provider | PASS |  | System Test
CHC007 |  | Verify that user can carry out airtime recharge | User should be able to successfully carry out airtime recharge | User was able to successfully carry out airtime recharge | PASS |  | System Test
CHC008 | View Wallet Transactions | Verify that User can download receipt once transaction is successful | The User should be able to download transaction receipt successfully | Transaction reciept could not be generated | FAIL | User was routed back to the services page | System Test
CHC009 | [6 empty] | System Test
CHC010 | [6 empty] | System Test
CHC011 | [6 empty] | System Test

## Defects
Defect ID | Test Case | Defects | Status | Reported Date | Resolution Date | Re-Test Date | Status | Comments | Developer's Comment
CHC003 | Fund Wallet | "Wallet is not available to receive funds was displayed" was displayed | Failed | 2021-03-03
CHC008 | View Wallet Transaction | Unable to view wallwt transaction | Failed | 2021-03-03